## Time Tracking
Date | Start | End | Task | Hours
Kick off & planning
2026-04-24 | 14:00 | 15:00 | Initial commit: repository setup, branching strategy | 1
2026-04-25 | 10:00 | 12:00 | Reading assignment brief, understanding project requirements and scope | 2
2026-04-27 | 09:00 | 12:00 | Project scaffold: Express server, client folder, config files, README | 3
Research
2026-04-28 | 13:00 | 15:30 | Research: 3d-force-graph library — API, options, Three.js integration | 2.5
2026-04-29 | 10:00 | 12:00 | Research: CouchDB concepts — document model, HTTP API, Fauxton UI | 2
2026-04-30 | 14:00 | 15:30 | Research: CORDIS Horizon data — inspecting Excel files, understanding schema | 1.5
2026-05-04 | 09:00 | 11:30 | CouchDB installation, admin user creation, CORS configuration (local.ini) | 2.5
2026-05-05 | 13:00 | 14:30 | Research: D3 force simulation — charge, link strength, forceCollide | 1.5
2026-05-06 | 10:00 | 11:30 | Designing CouchDB document schema: type field, _id conventions, link model | 1.5
2026-05-07 | 14:00 | 15:30 | Research: Node.js async/await patterns, Express 5 routing, fetch API | 1.5
Development
2026-05-12 | 09:00 | 12:00 | CouchDB import script design, couchdb-setup.md documentation (c2e96dd) | 3
2026-05-13 | 09:30 | 13:00 | feat: Excel -> CouchDB import script + inspect tool; added xlsx + minimist deps | 3.5
2026-05-14 | 14:00 | 16:30 | Testing import script: dry run, debugging field mappings, running full import | 2.5
2026-05-15 | 09:00 | 12:00 | feat: replace dummy graph with real nodes and links from CouchDB | 3
2026-05-18 | 09:00 | 14:00 | feat: render graph from API data, connect live data, preview size limit | 5
2026-05-19 | 13:00 | 15:00 | Testing live graph with full dataset; tuning charge, node size, colours | 2
2026-05-20 | 09:00 | 13:30 | feat(ui): preview/full toggle, text filter, sampling slider, link weights | 4.5
2026-05-21 | 14:00 | 16:00 | Testing filter/preview features; debugging sampler edge cases | 2
2026-05-26 | 10:00 | 11:30 | Research: 3d-force-graph particle API, linkDirectionalParticles options | 1.5
2026-05-27 | 09:00 | 16:00 | feat(ui): directional particles, graph fetch fix, header CSS, particle slider | 7
2026-05-28 | 09:00 | 13:00 | feature(pin): pin functionality with glow; fix(caching): 304 graph blank | 4
2026-05-29 | 10:00 | 13:00 | fix(clusters): buildClusteredGraph, aggregated links, pin/cluster interaction | 3
2026-05-30 | 14:00 | 15:30 | Manual testing: pin persistence across reload, cluster expand/collapse edge cases | 1.5
2026-06-01 | 09:30 | 11:30 | Research: 3d-force-graph onNodeClick / onNodeHover / onLinkClick API | 2
2026-06-03 | 14:00 | 15:30 | Designing node detail panel: field layout per type, CSS variables, chip styles | 1.5
2026-06-06 | 10:00 | 12:30 | fix(graph loading): reusable fetch functions; silent CouchDB failure root-cause | 2.5
2026-06-07 | 14:00 | 16:00 | Debugging fetch refactor; scoping node interaction implementation | 2
2026-06-08 | 09:00 | 17:30 | fix(fetching) + feat(node interaction): single fetch, panel, highlights, tooltips | 8
2026-06-09 | 10:00 | 12:00 | Testing node/link click panel; verifying highlight + tooltip across all types | 2
2026-06-10 | 09:00 | 12:00 | feat/refactor(filtering): applyAllFilters, filterState, chips, datalists | 3
2026-06-10 | 13:00 | 16:30 | cleanup/fix: duplicate function declarations, inconsistent variable names, CSS | 3.5
TOTAL HOURS |  |  |  | 86